## Sheet1
Task Name: (Dependencies top to bottom) | [8 empty] | Justin | Thomas | Kole | Ozzie | Sushant | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task
Preliminary &
| Requirements |  |  |  |  | 8 |  | 9 |  |  |  |  | 0
|  | Gather | Requirements Engineer | Ozzie | 2 |  | 3 |  |  |  |  | 3 |  | 3 | Done individually
|  | Analyze | Requirements Engineer | Ozzie, Justin, Thomas, Sushant, Kole | 3 |  | 3 |  | 3 | 3 | 3 | 3 | 3 | 15 | As a Team
|  | Specify | Requirements Engineer | Ozzie, Justin, Thomas, Sushant, Kole | 3 |  | 3 |  | 3 | 3 | 3 | 3 | 3 | 15 | As a Team
| Documentation |  |  |  |  | 13 |  | 21 |  |  |  |  | 0
|  | Project Charter | Project Manager | Ozzie | 2 |  | 3 |  | 0 |  |  | 3 |  | 3 | Done individually
|  | Release Branches | Project Manager | Thomas, Justin, Ozzie, Sushant, Kole | 1 |  | 3 |  | 2 | 1 | 1 | 1 | 1 | 6 | Done during class, with Ozzie, Thomas, Kole, and Sushant. Justin completed indivdually
|  | Requirements Document | Project Manager, Requirements Engineer | Ozzie, Thomas | 5 |  | 10 |  |  | 2 |  | 8 |  | 10 | These were done seperatly and not during a group session. However, they were reviewed as a group following completion.
|  | Project Plan | Project Manager, Developers | Ozzie | 5 |  | 5 |  | 0 |  |  | 5 |  | 5 | Done individually
Coding | [6 empty] | 0 | [5 empty] | 0
Iteration 1: | Development |  |  |  |  | 24 |  | 66 |  |  |  |  | 0
|  | Determine technology needs | Developer | Justin, Thomas, Kole, Ozzie, Sushant | 2 |  | 17 |  |  | 5 | 5 | 2 | 5 | 17 | Done Seperately
|  | Research and learn new language and environment | Developer | Thomas, Kole, Sushant | 20 |  | 47 |  |  | 21 | 13 |  | 13 | 47 | These were done seperately
|  | Evaluate needs for next iteration | Project Manager | Ozzie | 2 |  | 2 |  |  |  |  | 2 |  | 2 | Done individually
Total | [5 empty] | 45 |  | 96 | 8 | 35 | 25 | 30 | 25 | 123